## Slide 1: SR 159 (BRIDGE STREET)
Tom Barnitz, ODOT Project Manager
2025 State of the Community

## Slide 2: Presentation overview
Project Location
Project Scope
Unique Work Items
Maintenance of Traffic
Aesthetics
Status & Schedule

## Slide 3: Project location
SR 159
Project Length: 1.12 miles

## Slide 4: Regional shopping and commercial district
  ROS-159 / US 35 - interchange with US 35
  US 23 (north-south)
  US 50 (east-west)
  Traffic comes from surrounding counties to this Regional Retail / Commercial District
  This is the reason for an accelerated construction schedule to get traffic lanes opened for Thanksgiving and Christmas shopping season.
Notes: Chris Chiles
Last piece of highway to complete connection of SR7
KYOVA’s Ohio River Bridge Crossing Study
Importance of SR7 in Regional Road Network from KYOVA’s perspective as MPO

## Slide 5: Project corridor issues
Safety
Crashes
Pedestrian Access
Congestion
North
Notes: Chris Chiles
Last piece of highway to complete connection of SR7
KYOVA’s Ohio River Bridge Crossing Study
Importance of SR7 in Regional Road Network from KYOVA’s perspective as MPO

## Slide 6: Roadway improvements
  Add new Northbound Lane from Stewart Rd to Pawnee Rd;
  Add new Southbound drop lane to US35 West ramp;
  Add new Marietta Rd (access road) behind Applebee's/Raising Cane’s;
  Add shared-use path and sidewalks both sides of street where feasible;
  Add Roundabout on Consumer Center Drive;
  Add turn lanes/Re-configure Stewart/Consumer Center Intersection; WB – dual RT lanes
  Interchange ramp re-alignment;
  Replace all of interchange pavement with all new 9” concrete;
  All new traffic signal poles, lights and signal control equipment at 7 intersections;
  Aesthetic enhancements – add pocket parks along corridor; paint bridge railing, replace poles and lights on bridge, roundabout plantings; add black steel fence; sandstone looking retaining wall
Notes: The Base Improvements that are proposed for all scenarios are:
  Adding a new Northbound Lane from Stewart to Pawnee
  Adding a new Southbound drop turn lane to US35 West
  Adding a new Access Rd behind Applebee's/Raising Cane’s
  Realignment of the Pawnee intersection, and
  Adding pedestrian facilities where feasible

## Slide 7: Additional Northbound Lane on Bridge Street
From north of the Scioto River bridge to Pawnee Rd
North
Notes: Bridge Street currently has two northbound lanes. With its dense commercial development, travelers driving through the corridor tend to avoid the right lane, which is continuously used for vehicles slowing down to turn right into the numerous driveways. This tendency overloads the left lane which creates congestion when volumes are high.
This project proposes to add a third northbound lane through the corridor, which will provide a second lane for the through vehicles to use in order to avoid the right lane. This will provide additional capacity and reduce delays in the corridor. The additional lane will lower vehicle delay for northbound drivers by 5-10 seconds. This may not seem like a significant reduction but given there are over 2000 vehicles per hour on this approach, it equates to nearly 6 hours of reduced delay per intersection. This is a substantial reduction.
ODOT is considering two options for how far north the new lane should go. We will discuss that later, under the project’s options for public comments.

## Slide 8: Additional Northbound Lane on Bridge Street
Ends at Chillicothe Mall entrance, north of Pawnee Rd.
North
McDonalds
Retaining Wall
Notes: Option 2 would install the additional lane an extra 1200 feet further north. There, the additional lane will drop off by becoming a right-turn only lane for the Chillicothe Mall entrance.

## Slide 9: Add drop lane to US35 westbound ramp
North
Notes: Another improvement that ODOT proposes to implement is to realign the southbound lanes on Bridge Street. Bridge Street has three southbound lanes through the project area. Currently, the right curb lane becomes overloaded by vehicles wanting to access local businesses on the west side of Bridge Street, waiting to use the westbound entrance ramp to US 35, and wanting to access the businesses located on Stewart Road and Consumer Center Drive. To further strain the situation, southbound vehicles tend to avoid the left lane because it becomes a dedicated turn lane to the US-35 eastbound on-ramp. During each day’s peak travel times, this puts over 2100 vehicles per hour in the two thru lanes.
The project proposes to realign the lanes so that vehicles can stay in the left two lanes for the full project corridor. At the US-35 interchange the right lane will become dedicated for the westbound onramp to US-35. A separate turn lane will be provided to access the eastbound US-35 on-ramp. These proposed changes will put 1800 vehicles per hour in the two thru lanes - a reduction of over 150 vehicles per lane.
This change will benefit traffic operations in the corridor.

## Slide 10: New Access Road between N. Plaza & Marietta
North
WALGREENS
Notes: ODOT also proposes to construct a new access road between North Plaza Boulevard and Marietta Road, to the west of Bridge Street. The US 35 WB exit ramp lines up directly across Bridge Street from N Plaza Boulevard. The intersection of Bridge Street and Marietta Road is located 500 feet north of this intersection. During peak traffic hours, traffic is often stopped between these two intersections with the backup extending beyond the next intersections. Because the traffic signal at North Plaza Boulevard must favor the US-35 exit ramp, long lines extend into the business park area west of Bridge Street. As a result, drivers have created their own go-around that cuts behind the BP gas station, Raising Cane’s and Applebee’s to get to the Marietta Road traffic signal by Walgreen’s. ODOT proposes to install a road that will make this go-around safer.

## Slide 11: Pedestrian Facilities
- 5.5’-7.5’ wide Sidewalk
- 10’-12’ wide Shared Use Path
North
STATE BIKE ROUTE 20

## Slide 12: Pedestrian Facilities
North
- 5.5’-7.5’ wide Sidewalk
- 10’-12’ wide Shared Use Path

## Slide 13: Pedestrian Facilities
North
- 5.5’-7.5’ wide Sidewalk
- 10’-12’ wide Shared Use Path
Retaining Walls

## Slide 14: Bridge St. / Stewart Rd. / Consumer Center Dr.
Notes: Option 3 proposes the same improvements as Option 2 regarding the restrictions of left and thru movements at Bridge Street and Stewart Road intersection. Option 3 offers one difference at the Stewart Road and Consumer Center Drive intersection: Instead of proposing a signal to handle the additional traffic that would be created at this intersection, a Single Lane Roundabout is proposed.

## Slide 15: Bridge St. / Stewart Rd. / Consumer Center Dr.
Notes: Option 3 proposes the same improvements as Option 2 regarding the restrictions of left and thru movements at Bridge Street and Stewart Road intersection. Option 3 offers one difference at the Stewart Road and Consumer Center Drive intersection: Instead of proposing a signal to handle the additional traffic that would be created at this intersection, a Single Lane Roundabout is proposed.

## Slide 16: US 35 Eastbound Exit Ramp to Bridge Street
Notes: The next set of options relate to the US-35 eastbound exit ramp to Bridge Street, as vehicles regularly back up on the ramp, and sometimes onto the eastbound lanes of US 35. Currently the ramp is configured with two left turn lanes onto northbound Bridge Street and a single, free-flow, right turn lane onto southbound Bridge Street.
A short-term improvement to address heavy backups is being installed later this year. ODOT is considering the two following options as long-term improvements. Option 1, shown in this exhibit, would maintain the same double left turn lanes and single right turn lane that currently exists for this ramp. However, this option eliminates the free-flow right turn lane from the ramp to southbound Bridge Street. In other words, all traffic on the ramp will need to use the traffic signal.

## Slide 17: Unique work items
  Full-depth concrete pavement - replacement at interchange and ramps
  Retaining walls (cast in place concrete (2)) and large modular block wall (~1 ton each block)
  Upsize some of storm sewer pipe and all new curb and gutter
  All new street lighting (LED), signage, traffic signals (7), striping, fencing, Emergency Vehicle pre-emption
  All new web-based central traffic management for signal coordination
  All new business drive entrances - concrete (many right-in/right-out)
  Material Only Contract – Signal and Light Poles ready for Year #1 construction
  Accelerated construction to open existing and new lanes to traffic by holiday shipping season

## Slide 18: Maintenance of traffic
Maintenance Of Traffic – Phase 1, 2, & 3 - first year
  Maintain traffic through interchange in both directions
  Interim Completion – Lanes open to traffic by 10/15/2025 with $15k/day Disincentive

## Slide 19: Maintenance of traffic
Maintence Of Traffic – Phase 1, 2, & 3 - first year
  Maintain traffic through interchange in both directions
  Interim Completion – Lanes open to traffic by 10/15/2025 with $15k/day Disincentive

## Slide 20: Maintenance of traffic
Maintenance Of Traffic – Phase 4, 5, & 6 - second year
  Maintain 2-3 lanes traffic through interchange in Northbound direction only
  Southbound detoured (except for west bound ramp to US 35)
  Interim Completion – Lanes open to traffic by 10/15/2026 with $15k/day Disincentive
Those in favor of this Alternative:
  B&N - (Engineering Consultant)
  ODOT - Roadway Engineering
  ODOT - District 9 Planning & Engineering
  Chillicothe Fire/EMS and Police – no Fire Station north of Scioto River & Hospital is north of town
Why? - Because all other alternatives were much worse!!

## Slide 21: Maintenance of traffic

## Slide 22: Maintenance of traffic

## Slide 23: detour

## Slide 24: detour

## Slide 25: detour

## Slide 26: aesthetics
LED Lamps – Bridge and Pocket Parks

## Slide 27: aesthetics

## Slide 28: aesthetics

## Slide 29: aesthetics
Pocket Park (Full)
Pocket Park (Half)
Pocket Park (Minimal)

## Slide 30: aesthetics

## Slide 31: aesthetics

## Slide 32: aesthetics

## Slide 33: aesthetics

## Slide 34: aesthetics
Large Block Retaining wall under US 35 bridge

## Slide 35: aesthetics
12’ Shared Use Path
9’ Sidewalk

## Slide 36: aesthetics
Black steel fence
Retaining walls with pattern and color to match Large Block retaining wall under US 35 bridge

## Slide 37: aesthetics

## Slide 38: Status & Schedule
Contractor – Complete General Construction
Construction Cost: $19.3 Million
Award Date: 2/21/2025
Lanes Open for Holiday shopping: Oct 15th-Nov 15th each year
Construction End: 7/2/2027
Signal and Light poles: Available for delivery mid-March 2025

## Slide 39: Thank you
Tom Barnitz, P.E.
tom.barnitz@dot.ohio.gov
740.774.8877
More Information?? - Go to ODOT Website and put in Project Number - 113013